## Sheet1
Milesstone | Expected Completion Date | Actual Completion Date | Reason if not completed
Create Base Site | 2020-10-17 | 2020-11-01
Creating the databse that will store the information | 2020-10-21 | 2020-11-01
Implementing database | 2020-10-27 | 2020-11-01
Creating the search function | 2020-11-02 | 2020-11-02
Search by ingredient/mixer | 2020-11-03 | Not completed yet, will be completed by mid-December | API had some limitations that I am currently working through to complete this feature
Login and age verification implementation | 2020-11-09 | Not completed yet, will be completed by 11/28/2020 | Other functions of the site started taking priority such as the random drink function and the full list function of the site. Also having issues implmenting database
Favorite drink function | 2020-11-09 | Not completed yet, will be completed by mid-December | Working through database to figure out implementation
Random Drink Function | 2020-11-10 | 2020-11-14
Full list function | 2020-11-15 | Not completed yet, will be completed by 11/28/2020 | API chosen was having issues in implementation,will be worked through